## Sheet1
Sprint ID | 2244
Sprint Name | Omni - 2021 - Sprint 8
Sprint Start | Mon, 07 Jun 21 09:21:28 +0500
Sprint End | Fri, 25 Jun 21 18:22:00 +0500
Sprint State | CLOSED on Mon, 28 Jun 21 10:26:30 +0500
Report Generated on | Wed, 14 Jul 21 23:32:52 +0500
|  |  | To Do |  | Open |  | In Progress |  | In Review |  | Done |  | Resolved |  | Completed
Task | Created On | State | Actual Time | Buisness Time | Actual Time | Buisness Time | Actual Time | Buisness Time | Actual Time | Buisness Time | Actual Time | Buisness Time | Actual Time | Buisness Time | Actual Time | Buisness Time | Resolved on
MELO-1201 | 2021-06-11 | Done | 33m | 33m |  |  | 21h,56m | 5h,7m | 3d,23h,55m | 2d,1h,44m | 9d,7h,38m | 7d,7h,16m
MELO-1200 | 2021-06-11 | Done | 30m | 30m |  |  | 21h,51m | 5h,11m | 4d,1h,13m | 2d,2h,53m | 9d,6h,29m | 7d,6h,7m
MELO-1199 | 2021-06-11 | Done | 37m | 37m |  |  | 21h,56m | 5h,7m | 3d,23h,55m | 2d,1h,44m | 9d,7h,38m | 7d,7h,16m
MELO-1198 | 2021-06-11 | Done | 39m | 39m |  |  | 21h,56m | 5h,7m | 3d,23h,55m | 2d,1h,44m | 9d,7h,38m | 7d,7h,16m
MELO-1197 | 2021-06-11 | Done | 38m | 38m |  |  | 21h,51m | 5h,11m | 4d,1h,13m | 2d,2h,53m | 9d,6h,29m | 7d,6h,7m
MELO-1196 | 2021-06-11 | Done | 40m | 40m |  |  | 21h,51m | 5h,11m | 4d,1h,32m | 2d,3h,12m | 9d,6h,10m | 7d,5h,48m
MELO-1195 | 2021-06-11 | Done | 41m | 41m |  |  | 21h,51m | 5h,11m | 4d,1h,14m | 2d,2h,54m | 9d,6h,28m | 7d,6h,6m
MELO-1194 | 2021-06-11 | Done | 47m | 47m |  |  | 21h,56m | 5h,7m | 3d,23h,55m | 2d,1h,44m | 9d,7h,38m | 7d,7h,16m
MELO-1193 | 2021-06-11 | Done | 46m | 46m |  |  | 21h,51m | 5h,11m | 4d,43m | 2d,2h,22m | 9d,7h | 7d,6h,38m
MELO-1192 | 2021-06-11 | Done | 53m | 53m |  |  | 21h,56m | 5h,7m | 3d,23h,55m | 2d,1h,44m | 9d,7h,38m | 7d,7h,16m
MELO-1191 | 2021-06-11 | Done | 57m | 57m |  |  | 21h,56m | 5h,7m | 3d,23h,55m | 2d,1h,44m | 9d,7h,38m | 7d,7h,16m
MELO-1190 | 2021-06-10 | Completed | 6d,12h,16m | 4d,3h,17m | 48m | 48m |  |  | 16h,21m | 1d | 18d,17h,50m | 12d,4h,9m |  |  | 0 | 0
MELO-1189 | 2021-06-10 | Completed | 8m | 8m |  |  | 5d,23h,47m | 3d,8h,47m | 1d,7h,30m | 1d,6h,12m | 14d,15h,59m | 10d,2h,16m |  |  | 0 | 0
MELO-1188 | 2021-06-07 | Completed | 2h,53m | 0 |  |  | 1h,21m | 0 |  |  | 24d,10h,56m | 18d,2h,18m |  |  | 0 | 0
MELO-1186 | 2021-06-07 | Done | 23h,55m | 8h,55m |  |  | 8d,1h,11m | 6d,1h,11m | 0 | 0 | 9d,55m | 7d,33m
MELO-1185 | 2021-06-07 | Done | 27m | 27m |  |  | 16d,41m | 12d,41m |  |  | 2d,55m | 2d,33m
MELO-1184 | 2021-06-07 | Done | 10m | 10m |  |  | 19h,10m | 4h,10m | 1d,3h,50m | 1d,3h,50m | 16d,3h | 12d,2h,38m
MELO-1183 | 2021-06-07 | Done | 22m | 22m |  |  | 7d,23h,26m | 5d,8h,26m | 2d,1h,42m | 2d,1h,42m | 8d,42m | 6d,20m
MELO-1182 | 2021-06-07 | Done | 21h,6m | 6h,6m |  |  | 7d,4h,48m | 5d,4h,48m | 1d,1h,15m | 1d,1h,15m | 9d,45m | 7d,23m
MELO-1181 | 2021-06-07 | Done | 8d,3h,1m | 6d,3h,1m |  |  | 2d,20h,30m | 2d,5h,30m | 1h,22m | 1h,22m | 7d,3h,11m | 5d,2h,49m
MELO-1180 | 2021-06-07 | Done | 8d,2h,6m | 6d,2h,6m |  |  | 2d,19h,44m | 2d,4h,44m | 3h,5m | 3h,5m | 7d,3h,11m | 5d,2h,49m
MELO-1176 | 2021-06-04 | Completed | 4d,23h,48m | 2d,8h,48m |  |  | 1d,23h,12m | 1d,8h,12m | 4d,23h,21m | 2d,8h,21m | 8d,18h,59m | 6d,3h,59m |  |  | 7h,12m | 6h,50m
MELO-1175 | 2021-06-03 | Done | 7d,8h,46m | 5d |  |  | 6d,20h,49m | 5d |  |  | 7d,15h,27m | 6d
MELO-1174 | 2021-06-03 | Done | 2h,10m | 0 |  |  | 5d,21h,12m | 3d,8h,38m | 8d,35m | 6d,22m | 8d,9m | 6d
MELO-1167 | 2021-05-27 | Done | 22h,11m | 7h,11m |  |  | 12d,1h,6m | 8d,1h,6m |  |  | 16d,3h,50m | 12d,3h,28m
MELO-1159 | 2021-05-19 | Done | 36d,19h,18m | 26d | [6 empty] | 21h,52m | 1d
MELO-1153 | 2021-05-17 | Completed | 20h,21m | 5h,21m |  |  | 21d,14h,32m | 14d,5h,47m | 13h,42m | 7h,27m | 30d,3h,58m | 22d,1h,33m |  |  | 0 | 0
MELO-1152 | 2021-05-12 | Done | 36d,4h,42m | 25d | [6 empty] | 7d,15h,8m | 6d
MELO-1151 | 2021-05-12 | Completed | 20d,10h,55m | 12d,5h,59m |  |  | 5d,8h,14m | 3d,8h,14m | 17d,6h,18m | 13d,3h,47m | 10d,14h,49m | 6d,2h,20m |  |  | 0 | 0
MELO-1139 | 2021-05-08 | Completed | 37d,16h,1m | 24d,7h,22m |  |  |  |  | 10d,4h,9m | 8d,1h,38m | 14d,21h,54m | 11d |  |  | 0 | 0
MELO-1138 | 2021-05-06 | Completed | 6d,15h | 4d,1h,29m |  |  | 27d,7h,40m | 18d,7h,32m | 16d,10m | 12d | 6d,48m | 4d |  |  | 0 | 0
MELO-1137 | 2021-05-06 | Done | 44d,19h,48m | 31d,3h,6m | [6 empty] | 19d,16h,17m | 14d
MELO-1135 | 2021-05-05 | Done | resolved |  | 9h,40m | 2h,37m | 43d,2h,38m | 30d | 5d,23h,51m | 4d | 1d,14h,50m | 2d
MELO-1113 | 2021-04-30 | Completed | 25d,3h,34m | 17d,3h,34m |  |  | 7d,3h,14m | 4d,14m | 23d,1h,14m | 17d,1h,29m | 7d,22h,32m | 6d |  |  | 0 | 0
MELO-1111 | 2021-04-29 | Done | 49d,10h,50m | 34d,1h,57m | [6 empty] | 7d,15h,28m | 6d
MELO-1101 | 2021-04-27 | Completed | 43d,13h,6m | 30d,6h,35m |  |  | 11m | 0 |  |  | 29d,19h,23m | 22d |  |  | 0 | 0
MELO-1089 | 2021-04-26 | Completed | 1h,17m | 1h,17m |  |  | 27d,20h,56m | 19d,5h,56m | 24d,3h,18m | 17d,3h,5m | 14d,5h,29m | 10d |  |  | 0 | 0
MELO-1085 | 2021-04-22 | Completed | 13d,21h,25m | 9d,6h,25m |  |  | 29d,8h,44m | 20d,1h,30m | 1d,1h,12m | 1d,1h,12m | 26d,22h,54m | 19d,4h,16m |  |  | 0 | 0
MELO-1084 | 2021-04-21 | Completed | 13d,9m | 9d,9m |  |  | 20d,21h,48m | 14d,59m | 14d,19h,5m | 10d,54m | 16d,1h,27m | 12d,1h,27m |  |  | 7h,2m | 6h,40m
MELO-1080 | 2021-04-21 | Completed | 18d,5h,22m | 12d,4h,48m |  |  | 3d,20h,25m | 3d,5h,25m |  |  | 57d,6h,31m | 40d,4h,37m |  |  | 0 | 0
MELO-1069 | 2021-04-14 | Completed | 29d,18h,23m | 21d,4h,13m |  |  | 14d,22h | 10d,7h,48m | 19d,5h,39m | 12d,4h,51m | 14d,20h,3m | 10d,5h,3m |  |  | 0 | 0
MELO-1067 | 2021-04-14 | Completed | 1d,10h,13m | 1d,43m |  |  | 49d,6h,52m | 34d,1h,22m | 21d,9h,24m | 15d,7h,38m | 6d,15h,4m | 4d,1h,50m |  |  | 0 | 0
MELO-1035 | 2021-03-24 | Done | 15d,21h,54m | 12d,6m |  |  | 53d,17h | 36d,4h,2m | 7d,7h,24m | 5d,4h,44m | 15d,23h,52m | 12d,8m
MELO-1008 | 2021-03-09 | Done | 42d,3h,9m | 30d,2h,23m |  |  | 19d,4h,46m | 13d,42m | 29d,13h,20m | 20d,3h,10m | 17d,6h,12m | 13d,5h,50m
MELO-972 | 2021-02-04 | Done | 32d,19h,15m | 22d,4h,15m |  |  | 51d,4h,11m | 37d,4h,11m | 49d,13h,1m | 34d,4h,9m | 7d,15h,30m | 6d
MELO-969 | 2021-02-04 | Done | 32d,20h,10m | 22d,5h,10m |  |  | 96d,10h,50m | 67d,8h,20m | 4d,6h,22m | 4d | 7d,15h,30m | 6d
MELO-968 | 2021-02-04 | Done | 124d,8h,41m | 87d,4h,32m |  |  | 4d,22h,32m | 3d | 2d,11h,43m | 2d | 9d,9h,59m | 8d
MELO-967 | 2021-02-04 | Done | 32d,20h,14m | 22d,5h,14m |  |  | 79d,2h,41m | 56d,2h,41m | 21d,14h,30m | 15d,5h,39m | 7d,15h,30m | 6d
MELO-926 | 2021-01-15 | Done | 147d,19h,7m | 104d,3h,15m |  |  | 4d,8h,24m | 3d | 7d,4h,3m | 5d | 1d,20h,3m | 2d
MELO-899 | 2020-12-28 | Done | 167d,15h,47m | 117d,1h,27m |  |  | 7h,5m | 7h,5m | 6m | 6m | 11d,45m | 9d,23m